## Worksheet
Task Name | Assigned By | Assigned To | Task Type | Assigned Date | Actual Start Date | Actual End Date | Employee Start At | Employee End At | Total Hour for This Task | Total Hour Per Day | Completed Hours | Description
Integrating the Put method for the user dashboard | Dilip P | Dilip P | Task | 18-06-2024 | 18-06-2024 | 18-06-2024 | 18-06-2024 | 19-06-2024 | 3.00 hours | 3 | 2 | Integrating the Put method for the user dashboard and writing the javascript code for integrating the backend code
Writing Put Api for the user dashboard | Dilip P | Dilip P | Task | 18-06-2024 | 18-06-2024 | 18-06-2024 | 18-06-2024 | 19-06-2024 | 5.00 hours | 5 | 2 | Writing Put Api for the user dashboard becasue for editing the user profile.
Creating the education table and reworking on the register api | Dilip P | Dilip P | Task | 19-06-2024 | 19-06-2024 | 19-06-2024 | 19-06-2024 | 19-06-2024 | 10.00 hours | 10 | 1 | Creating the education table and reworking on the register api
Reworking on the user dashboard integration of post method | Dilip P | Dilip P | Task | 20-06-2024 | 20-06-2024 | 20-06-2024 | 20-06-2024 | 20-06-2024 | 11.00 hours | 11 | 1 | Reworking on the user dashboard integration&nbsp;of post method&nbsp;
Reworking on the apply job api and writing the javascript code | Dilip P | Dilip P | Task | 20-06-2024 | 21-06-2024 | 21-06-2024 | 20-06-2024 | 20-06-2024 | 10.67 hours | 10.67 | 1 | Reworking on the apply job api and writing the javascript code becasue the apply njob should be updated as per the cookies only&nbsp;
Integrating education model in user dashboard | Dilip P | Dilip P | Task | 21-06-2024 | 21-06-2024 | 21-06-2024 | 21-06-2024 | 22-06-2024 | 3.50 hours | 3.5 | 1 | Integrating education model in user dashboard writing javascript code for&nbsp;Integrating to backend code&nbsp;