## Worksheet
Task Name | Assigned By | Assigned To | Task Type | Assigned Date | Actual Start Date | Actual End Date | Employee Start At | Employee End At | Total Hour for This Task | Total Hour Per Day | Completed Hours | Description
dashboard | Anusiya M | Jayamani M | Task | 10-06-2024 | 10-06-2024 | 10-06-2024 | 11-06-2024 | 11-06-2024 | 1.00 hours | 1 | 1 | gh
bug solving | Jayamani M | Jayamani M | Task | 11-06-2024 | 11-06-2024 | 11-06-2024 | 11-06-2024 | 11-06-2024 | 7.00 hours | 7 | 1 | jiffy bug solving in the project manager pannel and tl and employee
report page content editing | Jayamani M | Jayamani M | Task | 17-06-2024 | 17-06-2024 | 17-06-2024 | 17-06-2024 | 17-06-2024 | 3.07 hours | 3.07 | 1 | Editing the content of a report page involves several key steps. First, conduct a thorough review of the existing content to ensure its relevance, accuracy, and clarity. Next, refine the structure by organizing the content logically to maintain a clear flow of information. Adjust the style and tone to align with the target audience and the report&#39;s purpose. Proofread meticulously to correct any grammar, punctuation, and spelling errors. Finally, enhance the visuals by integrating charts, tables, and images to support the text and improve overall readability.
leave management system backend logic | Jayamani M | Jayamani M | Task | 18-06-2024 | 18-06-2024 | 18-06-2024 | 18-06-2024 | 18-06-2024 | 2.15 hours | 2.15 | 1 | User Authentication: Validate user credentials and assign roles (employee, manager, admin). Leave Requests: Allow employees to submit leave requests with details (dates, type, reason). Approval Workflow: Route requests to managers for approval or rejection based on company policies. Leave Balance: Update employee leave balances and track usage and remaining leaves.
Signup - Employee - My task - Add task - Assign task for an employee who is busy at particular time - A message stating "Employee is busy during this time" should be displayed | Vaibhavi Khiranand Dhadde | Jayamani M | Bug | 18-06-2024 | 18-06-2024 | 18-06-2024 | 18-06-2024 | 18-06-2024 | 0.48 hours | 0.48 | 1 | &nbsp;Signup - Employee - My task - Add task - Assign task for an employee who is busy at particular time - A message stating &quot;Employee is busy during this time&quot; should be displayed Steps to reproduce bug&nbsp; 1.Navigate to website - https://jiffy.mineit.tech/jiffy/project/task.php 2.Select project name, Select module, enter task name, enter start time, due time, Select assign to, enter description and click on submit Test data&nbsp; Jiffy Digital Office, Employee, task, 10:00, 19:00, Vaibhavi Khiranand dhadde, test description Jiffy Digital Office, Employee, task, 10:00, 12:00, Vaibhavi Khiranand dhadde, test description Expected result: Proper message stating &quot;Employee will be busy during&nbsp; this time (10:00 - 19:00)&nbsp; should be displayed Actual result Task has been added successfully without error browser - Edge os - windows 11 version 22H2
Daily Report | Jayamani M | Jayamani M | Task | 18-06-2024 | 18-06-2024 | 18-06-2024 | 18-06-2024 | 18-06-2024 | 0.58 hours | 0.58 | 1 | Daily Report to get all the employee report based on the team members
signup - employee - Meeting - schedule meeting - user should feel easy to end the meeting | Vaibhavi Khiranand Dhadde | Jayamani M | Improvement | 18-06-2024 | 18-06-2024 | 20-06-2024 | 18-06-2024 | 18-06-2024 | 1.95 hours | 0.65 | 1 | signup - employee - Meeting - schedule meeting - user should feel easy to end the meeting Steps to reproduce bug: 1.navigate to website - https://jiffy.mineit.tech/jiffy/project/timeline.php 2.go to meeting 3.schedule meeting :Select project name, Start Time, End Time, Select meeting type, Enter meeting link, Select employee, Enter subject 4.generate MOM 5.End the meeting Test data : Jiffy digital office, 10:00, 12:00, Online,&nbsp;https://zoom.us/j/1234567890, Vaibhavi, test1 Expected result: Meeting should be scheduled initially the status of meeting should be &#39;Pending&#39; , after starting MOM status should change as &#39;In progress&#39;&nbsp; and&nbsp; meeting should be ended after uploading MOM This process of ending the meeting has many steps user will not get this easily. There should be a button called &#39;Set Action&#39; there user should be able to change the status of meeting as &#39;Pending&#39; , &#39;Inprogress&#39; or &#39;Ended&#39; Actual result: User will not get to know that how to end the meeting It is not userfriendly. browser - Edge os - windows 11 version 22H2 &nbsp;
signup - employee - My task - Add task - Leave description field(mandatory field) empty and try to submit - User should receive proper error message | Vaibhavi Khiranand Dhadde | Jayamani M | Bug | 18-06-2024 | 18-06-2024 | 20-06-2024 | 18-06-2024 | 18-06-2024 | 1.50 hours | 0.5 | 1 | signup - employee - My task - Add task - Leave description field(mandatory field) empty &nbsp;and try to submit - User should receive proper error message steps to reproduce bug 1.navigate to website - https://jiffy.mineit.tech/jiffy/project/task.php 2.go to My task - Add task 3.Select project name, select module, task name, type, actual start date, actual due date, select start time, select due time,Assign to, leave the description field empty and click on submit&nbsp;&nbsp; Expected result: Proper error message stating &quot;Please Fill out this field&quot; should be displayed near to &#39;Description field&#39; Actual result: Error message has not been displayed task has been assigned successfully. browser - Edge os - windows 11 version 22H2 &nbsp;
login - employee - Meeting - Schedule - Leave all fields empty click on submit - page should prompt user to fill out mandatory fields | Vaibhavi Khiranand Dhadde | Jayamani M | Bug | 19-06-2024 | 19-06-2024 | 21-06-2024 | 19-06-2024 | 19-06-2024 | 1.70 hours | 0.57 | 1 | login - employee - Meeting - Schedule - Leave all fields empty click on submit - page should prompt user &nbsp;to fill out mandatory fields Test steps: Navigate to website - https://jiffy.mineit.tech/jiffy/project/dashboard.php go to meeting - Click on schedule&nbsp; Leave all the fields empty and click on submit&nbsp; Expected result: Proper error message stating &quot;Please fill out this field&quot; should be displayed near the mandatory field Actual result Redirected to other page browser - edge os- windows 11 version 22H2
login - employee - Meeting - schedule meeting - Go to edit - form should not be edited successfully is any mandatory field is cleared | Vaibhavi Khiranand Dhadde | Jayamani M | Bug | 19-06-2024 | 19-06-2024 | 21-06-2024 | 19-06-2024 | 19-06-2024 | 3.55 hours | 1.18 | 1 | login - employee - Meeting - schedule meeting - Go to edit - form should not be edited successfully is any mandatory field is cleared Test steps: navigate to website - https://jiffy.mineit.tech/jiffy/dashboard.php go to meeting - Schedule - Schedule an online meeting with an employee&nbsp; Go to edit - Clear meeting link field and enter space in the subject field try to submit Test data: Select project name -&nbsp;&nbsp;jiffy digital office Select start time - 10:53 Select end time - 11:00 Select meeting type - Online&nbsp; Meeting link -&nbsp; Subject -&nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; Expected result : Proper error message should be displayed meeting should not be edited Actual result : Meeting edited successfully browser - edge os - windows 11 version 22H2&nbsp;
login - employee - Meeting - Schedule - Enter start time and End time before start date - Meeting should not be scheduled | Vaibhavi Khiranand Dhadde | Jayamani M | Bug | 19-06-2024 | 19-06-2024 | 21-06-2024 | 19-06-2024 | 19-06-2024 | 3.00 hours | 1 | 1 | login - employee - Meeting - Schedule - Enter start time and End time before start date - Meeting should not be scheduled Test steps: Navigate to website - https://jiffy.mineit.tech/jiffy/project/dashboard.php go to meeting - Schedule - Enter end time before start time try to submit Test data: Select Project name - Jiffy digital office Start time - 18-06-2024 End time - 17-06-2024 Select meeting type - offline Location - Meeting room Select employee - vaibhavi Enter subject - test Expected result - Meeting should not be scheduled proper error message stating &quot;Enter valid time&quot; should be displayed Actual result - Meeting has been scheduled successfully browser - edge os - windows 11 version 22H2
SEO | Jayamani M | Jayamani M | Task | 19-06-2024 | 19-06-2024 | 19-06-2024 | 19-06-2024 | 19-06-2024 | 1.00 hours | 1 | 1 | SEO&mdash;short for&nbsp;search engine optimization&mdash;is about helping search engines understand your content, and helping users find your site and make a decision about whether they should visit your site through a search engine.
Create Report for team and make formate Excel | Jayamani M | Jayamani M | Task | 19-06-2024 | 19-06-2024 | 19-06-2024 | 19-06-2024 | 20-06-2024 | 0.73 hours | 0.73 | 1 | Create Report for team progress and make formate as Excel&nbsp; and pdf
signup - employee - Report - generate report - Report should get created | Vaibhavi Khiranand Dhadde | Jayamani M | Bug | 19-06-2024 | 19-06-2024 | 21-06-2024 | 19-06-2024 | 20-06-2024 | 2.70 hours | 0.9 | 1 | signup - employee - Report - generate report - Report should get created Steps to reproduce bug: 1.navigate to website - https://jiffy.mineit.tech/jiffy/project/dashboard.php 2.go to report&nbsp; 3.enter valid start time, valid end time, Select employee - click on generate report Expected result: report should get generated&nbsp; Actual result: After clicking on generate report it is displaying a popup asking to select report type after selecting the report type as pdf/excel report is not getting generated browser - edge os - windows 11 version 22H2
login - employee - report - Enter end date before start date - before dates should be disabled | Vaibhavi Khiranand Dhadde | Jayamani M | Bug | 19-06-2024 | 19-06-2024 | 21-06-2024 | 22-06-2024 | 22-06-2024 | 2.50 hours | 0.83 | 1 | login - employee - report - Enter end date before start date - before dates should be disabled steps to reproduce bug: 1.navigate to website - https://jiffy.mineit.tech/jiffy/project/dashboard.php 2.go to report - enter start date , enter end date before start date Test data: Start date - 19-06-2024 End date - 04-06-2024 Expected result - Previous dates should be disabled or proper message stating &quot;end date can be 19-06-2024 or later&quot; Actual result - It has taken invalid end date without error browser - edge os - windows 11 version 22H2
login - employee - report - search here field displays proper message when no matching results found | Vaibhavi Khiranand Dhadde | Jayamani M | Bug | 19-06-2024 | 19-06-2024 | 21-06-2024 | 22-06-2024 | 22-06-2024 | 1.50 hours | 0.5 | 1 | login - employee - report - search here field displays proper message when no matching results found Steps to reproduce bug: 1.navigate to website - https://jiffy.mineit.tech/jiffy/project/dashboard.php 2.go to report - search here - 1.Enter some text in search field which is not present in dataset&nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp;- 2.Enter leading and trailing spaces with valid data 3. hit enter Test data - Search here - asddfdfg Expected result - 1.Proper message stating &quot;No matching records found&quot; should be displayed &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; 2.leading and trailing space should be trimmed and proper result should be displayed. Actual result - 1.No message has been displayed &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp;2.leading and trailing spaces are not trimmed proper result has not been displayed browser - edge os - windows 11 version 22H2
Login - employee - My task - Assign some task - go to task and change status - page should redirect to previous page after submitting changes | Vaibhavi Khiranand Dhadde | Jayamani M | Improvement | 20-06-2024 | 20-06-2024 | 22-06-2024 | 22-06-2024 | 22-06-2024 | 3.00 hours | 1 | 1 | Login - employee - My task - Assign some task - go to task and change status - page should redirect to previous page after submitting changes steps to reproduce bug: 1.navigate to website - https://jiffy.mineit.tech/jiffy/project/dashboard.php 2.go to my task 3.Click on add task - assign some task to yourself 4.go to the assigned task - change the status of task as &#39;in progress&#39; expected result - changes should be submitted successfully and user should redirect to previous page Actual result - changes submitted successfully but previous page has not been displayed browser - edge os - windows 11 version 22H2
Login - employee - My task - Add task - Attachments field should display proper error message on browsing more than allowed sized file | Vaibhavi Khiranand Dhadde | Jayamani M | Bug | 20-06-2024 | 20-06-2024 | 22-06-2024 | 22-06-2024 | 22-06-2024 | 3.00 hours | 1 | 1 | Login - employee - My task - Add task - Attachments field should display proper error message on browsing more than allowed sized file steps to reproduce bug: 1.navigate to website - https://jiffy.mineit.tech/jiffy/project/dashboard.php 2.go to my task - add task - &#39;select project&#39;, &#39;select module&#39;, &#39;task name&#39;, &#39;type&#39;, &#39;actual start date&#39;, &#39;actual due date&#39;, &#39;select start time&#39;, &#39;select due time&#39;, &#39;select assign to&#39;&nbsp; 3. attachments - browse a file which has more size than allowed size limit - click on submit Test data - &#39;Jiffy Digital Office&#39;, &#39;Empployee&#39; , &#39;test task&#39; , &#39;bug&#39;, &#39;20-06-2024&#39;, &#39;20-06-2024&#39;, &#39;14:58&#39;, &#39;14:59&#39;, &#39;vaibhavi&#39; Expected result: proper error message stating &quot;Please browse less than or 5MB file&quot; should be displayed Actual result: message not displayed. browser - edge os - windows 11 version 22H2 &nbsp;
Login - employee - My task - add task - select project name as 'Others' - select module should displays default option as placeholder | Vaibhavi Khiranand Dhadde | Jayamani M | Bug | 20-06-2024 | 20-06-2024 | 22-06-2024 | 20-06-2024 | 22-06-2024 | 3.00 hours | 1 | 2 | Login - employee - My task - add task - select project name as &#39;Others&#39; - select module should displays default option as placeholder steps&nbsp; to reproduce bug: 1.navigate to website - https://jiffy.mineit.tech/jiffy/project/dashboard.php 2.go to my task - add task 3.Select project name as &#39;Others&#39;&nbsp; Expected result - placeholder should be displayed for &#39;Select module&#39; dropdown Actual result - placeholder is not displayed for &#39;Select module&#39; dropdown after select project name as &#39;Others&#39; browser - edge os - windows 11 version 22H2 &nbsp;
Login - employee - Manage leave - Apply leave - proper error message should be displayed near the field when any mandatory field is kept empty | Vaibhavi Khiranand Dhadde | Jayamani M | Bug | 20-06-2024 | 20-06-2024 | 22-06-2024 | 20-06-2024 | 20-06-2024 | 3.00 hours | 1 | 1 | Login - employee - Manage leave - Apply leave - proper error message should be displayed near the field when any mandatory field is kept empty Steps to reproduce bug: 1.navigate to website - https://jiffy.mineit.tech/jiffy/project/dashboard.php 2.go to manage leave - apply leave - select leave type, leave from, leave to 3. leave the description field empty click on submit. Test data -&nbsp; casual leave, 20-06-2024, 20-06-2024 Expected result - Proper error message stating &quot;Description field cannot be empty&quot; should be displayed near the decsription field. Actual result - navigated to other page and displayed error message browser - edge os - windows 11 version 22H2